## Document Info
Audit Information
Column1 | Column2
Project Name: | <<Name of the Project to be audited>>
Project Code: | <<Acronym used for the project>>
PM Name: | <<Name of Project Manager>>
Auditor Name: | <<Name of Auditor>>
Audit Date: | <<Month DD, YYYY>>

## Internal Audit Checklist
INTERNAL AUDIT CHECK LIST FOR PROJECT MANAGEMENT
|  |  | Project Total Score | 72.6316
Sr.# | Query | SDLC Model | Possible Evidence | Verified | Total Points | Points Attained | Exception/ Deviation | NC # | Observation and Remarks
| Project Initiation |  |  |  | 5 | 5
1 | Did the PM validated the size and cost of the project on the basis of available information at high level? | All | Updated High Level Estimation Sheet | YES | 2 | 2 |  |  | Estimation sheet
2 | After signing the contract/work order, did PM develop the Project Definition Document and send it to organizational CC/ CM Lead. | All | PDD, sending email | YES | 1 | 1 |  |  | PDD Present
3 | Was project created in Issue Management System by the IMS admin. | All | IMS | YES | 1 | 1 |  |  | IMS present
4 | Was email for commencement of the project sent by the Manager Projects/Competency Lead/Competency Director to the relevant stakeholders (QA Competency, Shared Services, Project Team,etc). | All | Email to Distribution List | YES | 1 | 1
| Project Planning |  |  |  | 10 | 4
1 | Did the PM document following in PMP?: Scope, Milestones, artifacts, Constraints and assumptions, formal decision on Exceptions (if required) | All | PMP | NO | 4 | 0
2 | Did the PM prepare a detailed Estimation Sheet with the help of Dev Lead & QA Lead? | Water Fall | Detailed Estimation sheet | YES | 2 | 2
3 | Did the PM prepare Project/Sprint Schedule in coordination with QA Lead and Dev Lead? | All | PS | YES | 2 | 2 |  |  | handle in JIRA
4 | Was Project/Sprint Schedule approved by management/customer | All | Review email, any comments | NO | 2 | 0
| Project Monitoring |  |  |  | 12 | 12
1 | Did the PM Published weekly status report covering the anticipated risk, on-hand issues, planned vs actual progress and plan for next reporting period? | All | Weekly Status Report | YES | 9 | 9 |  |  | Daily Status report shared.
2 | Did the Project Manger conduct a project/Sprint status review meeting with Project Team to discuss the status report on a weekly basis? | All | MOMs, Updated Weekly Status report | YES | 3 | 3 |  |  | Monthly status report shared with Customer.
| Requirement Analysis |  |  |  | 15 | 10
1 | Were the FS/User Stories created to cover the whole scope of project/ Project Back log? | All | FSD/FDD/User Story | YES | 7 | 5 |  |  | Documents present in JIRA
2 | Was FS/User Stories reviewed & approved by client? | All | Review comments, approval email | YES | 5 | 5 |  |  | Customer signed copy present
3 | UX is reviewed and approved by the Client? | All | Review comments, Approval email | YES | 3 | 3
| Change Management |  |  |  | 8 | 8
1 | Were all changes proposed by client went through the formal review/ impact analysis cycle before implementation? | All | IMS, any other report/ document | YES | 8 | 8
| Technical Design |  |  |  | 8 | 0
1 | Did Technical Design reviewed and approved by architecture group? | All | Review comments, Approval email | NO | 8 | 0
| Code Writing |  |  |  | 7 | 7
1 | Did the PM/ Dev TL used the Static code analysis tool for the project? | All | Tool Reports | N/A | 0 | 0
2 | Did the Dev TL set up the Build Pipeline? | All | Development environment | YES | 3 | 3
3 | Was logic reviewed in code review process? | All | Code Review Comments | YES | 4 | 4 |  |  | Static code review done.
| Unit Testing |  |  |  | 10 | 10
1 | Did each member of the development team write unit tests? | All | Unit test cases | YES | 10 | 10 |  |  | Unit testcases present
| Internal Release |  |  |  | 7 | 4
1 | Is Release Management Plan is Published and being followed? | All | Release Management Plan | NO | 3 | 0
2 | Did the Dev team prepare build for the start of testing that includes code? If yes, did it contain DB scripts and installation instructions to deploy the code? | All | Internal Release Notes/ Internal Release email | YES | 2 | 2
3 | Did the Dev Team prepares the initial internal shipment package and notify the QA to process the shipment? | All | Internal shipment package, Notification email | YES | 2 | 2
| Test Planning & Designing |  |  |  | 4 | 2
1 | Is Test Plan Created? | All | Test Plan | N/A | 0 | 0
2 | Did QA share Release Acceptance Criteria with relevant stakeholders? | All | Communication email | NO | 1 | 0 |  |  | No acceptance criteria
3 | Was the project created in defect tracking tool by QA TL? | All | Defect Tracking Tool | YES | 1 | 1 |  |  | JIRA used for defect tracking
4 | Did QA team prepared test cases? | All | Test Cases | YES | 1 | 1
5 | Was mandatory test data prepared and documented in test cases? | All | Test Cases | NO | 1 | 0
| QA Acceptance & System Testing |  |  |  | 9 | 7
1 | Is QA provided separate Environment for Testing? | All | Testing Environment | YES | 2 | 2
2 | Was Acceptance Testing performed? | All | Execution Log, Updated AAC, acceptance/closure email | NO | 2 | 0
3 | Was System Testing performed? | All | Execution Log, Defects in Defect tracking tool | YES | 2 | 2
4 | Were all test cases executed? | All | Test Case Execution log | YES | 2 | 2
5 | Were defects tracked to closure? (Defect Resolution Life cycle) | All | Defects status in Defect tracking tool | YES | 1 | 1
[5 empty] | 95 | 69
0

## Audit Summary
Audit Summary Report
General Information
Location | Karachi | Project Manager | Umer Imtiaz | Remarks / Comments
Competency | Digital Framework | Development Lead | Muhammad Aqib
Track | BPM | QA Lead | Faizan Junani
Customer | Higher Education Commission | Auditor | Arsalan Rashid
Project | BPAS | Audit Date | 2019-03-07
Number of NC | 4
Audit Summary
Project Process Compliance % |  | 72.6316
Phase wise compliance |  |  |  | Phase need Attention
Query | Total Points | Points Attained |  | Technical Design
Project Initiation | 5 | 5 |  | Internal Release
Project Planning | 10 | 4
Project Monitoring | 12 | 12
Requirement Analysis | 15 | 10
Change Management | 8 | 8
Technical Design | 8 | 0
Code Writing | 7 | 7
Unit Testing | 10 | 10
Internal Release | 7 | 4
Test Planning & Designing | 4 | 2
QA Acceptance & System Testing | 9 | 7
NC # 1
Non Conformance Summary | No technical design /review practice in place
Type | Major
Phase | Technical Design
Owner | Technical Lead/Architect
NC # 2
Non Conformance Summary | No internal release planning practice in place
Type | Major
Phase | Internal Release
Owner | Technical Lead
NC # 3
Non Conformance Summary | PMP not in updated template
Type | Minor
Phase | Project Planning
Owner | Project Manager
NC # 4
Non Conformance Summary | QA team not preparing Acceptance Criteria
Type | Minor
Phase | QA Planning and Design
Owner | QA Lead
Sr # | Observations
1 | Test data should be prepere for detail testing
2 | Code review should be done by senior dev
3 | Test case review practice should be introduce
4

## Sheet1 (hidden)
YES | 0
NO | 1
N/A | 2
3
4

## Projects (hidden)
Competency | Project Name | Job Code | Project Manager/ Lead
E-Commerce
| Hobnob-E Commerce Website Deve | 356-003
| VSI EdgeAX CommerceLink | 003-156
| Tulo.com Implementation-Matt | 295-027
BI
| TRIPPS BI | 182-009
| Regeneron - CDW Development | 350-005
TS
| Ally Bank - VLR Implementation | 301-001
| Conestoga Title Insurance | 378-001
| Chatbot Product Dev | R016
ERP
| APF- B&H ERP Impl | 240-003
| QPM - Dynamics AX 2012 R3 Upgr | 144-138
BPM & Middleware
. | Telenor - Payment Gateway | 115-010